## 1. Scope Summary
GEB CVE Remediation — CN Portal ¦ Test Scope
August 2026 release. This document defines the test scope derived from the specific library changes in this release. Testing is bounded by what has changed. Portal areas not touched by the library changes below do not require re-regression as part of this release.
Item | Detail
Release | GEB CVE Remediation — August 2026
Market | CN (China)
Component | GEB Portal — applicable to both the bank-facing and customer-facing EAR variants
Scope | 8 actual libraries and 12 companion dependencies
Delivery mechanism | Hotfix for new and target-version JARs; written removal notes for superseded JARs
Delivery status | Hotfix prepared and available for SIT deployment
Wipro QC completed | Build validation, EAR packaging, deployment on UNIX DEV, Portal boot and basic operations verified. No boot-up or compilation errors.
Basis of this scope | Each test below traces to a documented change in the library release notes. Sources are listed in sheet 4.
Applicability note | Nimbus JOSE+JWT 9.x shades its internal JSON dependency. The applicability of the json-smart and accessors-smart companion entries is under confirmation. Any scope adjustment will be communicated before SIT deployment.

## 2. Test Scope by Library
Test Scope — derived from library changes
Each row states the documented change, the verification Wipro performs, and the corresponding business validation requested from the bank. Bank validation is anchored to a specific library touchpoint.
Ref | Library | Documented change in this version | Wipro verification | Bank validation requested | Expected result | Priority
T-01 | commons-fileupload 1.5 → 1.6 | A new limit, partHeaderSizeMax, is introduced with a default of 512 bytes applied to each individual multipart header. It replaces the previous limit, which applied to the header section as a whole. | Measure the Content-Disposition header length produced by the longest filename the Portal accepts, including non-ASCII filenames. Confirm it remains within the new limit, and configure the limit explicitly if required. | Attachment upload across Trade and Cash services, including files with long and non-ASCII (Chinese) filenames. Touchpoint: commons-fileupload | Uploads complete successfully. No rejection of filenames that are accepted today. | High
T-02 | commons-fileupload 1.5 → 1.6 | Uploads using content type multipart/related are now supported. | Confirm no existing Portal flow relies on multipart/related being rejected. | Attachment upload behaviour is unchanged for all currently supported content types. Touchpoint: commons-fileupload | No change in behaviour for existing upload flows. | Low
T-03 | commons-io 2.11 → 2.14 | Minor version upgrade, delivered as a companion to commons-fileupload. | Verify stream handling, byte counting and content-length calculation on file download and CSV export paths. | Account statement, account summary, transaction inquiry and report CSV/PDF/XLS export. Include Unicode characters, special characters and large datasets. Touchpoint: commons-io | Exports generate correctly. Encoding, byte counts and content-length are accurate. | Medium
T-04 | nimbus-jose-jwt 7.9 → 9.37.4 | The return type of Payload.toJSONObject() and JWSHeader.toJSONObject() changed from JSONObject to Map<String, Object>. JSON Smart classes no longer appear in the public API from version 9.0 onward. | Confirm the Portal compiles and runs against the target version, and that JWT claims are read correctly from the revised return type. | Login and authentication, including 1FA and 2FA. OTP validation. Logout and session termination. Session recovery. Touchpoint: nimbus-jose-jwt | Authentication completes successfully. Tokens are issued, parsed and verified without error. | High
T-05 | nimbus-jose-jwt 7.9 → 9.37.4 | Two major versions crossed. The JWS/JWE handling, JWK handling and signature verification surface are affected. | Exercise JWT generation, JWT validation, JWS detached signature, keystore validation, alias rotation, expired token handling and invalid signature handling. | One representative authenticated business transaction, confirming a token issued by the upgraded library is accepted end to end. Touchpoint: nimbus-jose-jwt | All security-component behaviours operate as before. Expired and invalid tokens are rejected as before. | High
T-06 | Spring family 5.3.27 → 5.3.34 (4 primary, 7 internal, 2 AspectJ) | Patch-level release within the 5.3.x line. Spring maintains binary compatibility across patch releases. No public API is removed or changed. | Compare the public API surface of the superseded and target JARs to confirm no removed or changed members. Verify clean application context initialisation and controller/endpoint registration. | Portal page rendering and request dispatch — smoke validation only. Touchpoint: Spring 5.3.34 A patch-level upgrade with no API change does not require full MVC regression. | Application context initialises cleanly. No startup exceptions. Endpoints register and respond. | Low
T-07 | json-smart 1.3.1 → 2.5.0 accessors-smart 2.5.0 (new) | Major version change. A JSON parsing depth limit of 400 is introduced. InputStream reading uses UTF-8. Reader and writer mappers are relocated. | Confirm applicability first (see the applicability note in sheet 1). If retained: verify JSON parsing depth and UTF-8 handling, and confirm no conflicting ASM library is present on the Portal classpath. | Applies only if these companions are retained. Validation folds into the authentication touchpoint above. Touchpoint: json-smart / accessors-smart | JSON payloads parse correctly, including Chinese characters. No classpath conflict on first token parse. | Medium
T-08 | activemq-core 5.4.1 (DECOMMISSION) | The library is removed from the EAR. It is not replaced. | Confirm the library is not referenced from Portal application code, Portal runtime configuration, or the deployment descriptor. Deploy the EAR without the library and confirm a clean boot. | Confirmation that no server-level component outside the EAR, and no external system integration, depends on this library being present on the classpath. Touchpoint: activemq-core | Portal boots cleanly. No ClassNotFoundException or NoClassDefFoundError. No functional impact. | Medium

## 3. Not in Scope
Not in scope for this release — with rationale
Recorded so that the boundary of this release is explicit and auditable.
Item | Position | Rationale
Velocity 1.7 | Not upgraded. No test cases. | The library is not modified by this release. Its residual CVE position and exploitability rationale are documented in the solution document. Testing an unmodified library falls outside the change-derived scope of this release.
log4j, batik, springfox, guava | Out of scope for CN. | Already at target version in the CN deployment. No change delivered.
Portal functions not listed in sheet 2 | No re-regression required. | The scope of this release is bounded by the library changes documented in sheet 2. Portal areas with no touchpoint to a changed library are unaffected.
Full Spring MVC regression | Not required. | Spring 5.3.27 to 5.3.34 is a patch-level upgrade with no public API change. Smoke validation of context initialisation and request dispatch is sufficient. Evidence is available on request.
Server configuration | No change required from bank operations. | The library changes reside within the EAR classpath. No change is required to standalone.xml, domain.xml, datasources, security realms or JBoss module definitions.
Detailed QA test cases | Provided separately. | A separate detailed test case document accompanies this scope and will be shared for the SIT/UAT cycle. This document defines the scope; that document defines the cases.

## 4. References
References — basis for each documented change
Each change stated in sheet 2 traces to the published release notes of the library concerned.
Library | Change | Source
commons-fileupload 1.6.0 | partHeaderSizeMax introduced, default 512 bytes per individual multipart header. Supersedes the previous whole-header-section limit. | Apache Commons FileUpload 1.6.0 release notes
commons-fileupload 1.6.0 | No client code changes required to migrate from 1.5 to 1.6. | Apache Commons FileUpload 1.6.0 release notes
commons-fileupload 1.6.0 | Support for uploads using content type multipart/related. | Apache Commons FileUpload 1.6.0 release notes
commons-fileupload 1.6.0 | Declares Commons IO 2.19.0. The pairing with Commons IO 2.14 in this release is a deliberate deviation, recorded for acknowledgement. | Apache Commons FileUpload 1.6.0 release notes
nimbus-jose-jwt 9.0 | JSON Smart is shaded and relocated. Its classes no longer appear in the public API. | Connect2id — Nimbus JOSE+JWT 9.0 release notes
nimbus-jose-jwt 9.37.x | Payload.toJSONObject() and JWSHeader.toJSONObject() return Map<String, Object> in place of JSONObject. | Vendor advisory documenting an upgrade to nimbus-jose-jwt 9.37.3
json-smart 2.x | JSON parsing depth limit of 400 introduced. InputStream reading uses UTF-8. Reader and writer mappers relocated. | json-smart project changelog
Spring Framework 5.3.x | Patch releases within a minor line maintain binary compatibility. No public API removal or change. | Spring Framework versioning policy; verified by API comparison of the superseded and target JARs