## Summary
GEB Platform Upgrade — Migration Effort Estimation
Wipro Consulting ¦ UOB Singapore ¦ Confidential ¦ April 2026
# | Layer / Component | Mandays (Dev) | PPT Reference | Complexity | Volume | Notes
1 | Layer 1 — Core Platform Migration
1.1 | Java 8 → Java 17 + javax→jakarta | 0 | Slide 2 — Stack Overview | Medium | High | Namespace changes across codebase
1.2 | JBoss EAP 7.3 → EAP 8 | 0 | Slide 2 — Stack Overview | Low | Low | Runtime + deployment config
1.3 | Turbine 2.3.3 → Turbine 7.0 | 0 | Slide 3 — Turbine | High | High | Framework redesign — RunData, pipeline, services
1.4 | Torque 3.1.1 → Torque 5.1+ | 0 | Slide 4 — Torque ORM | Medium | Low | Criteria API, Village, Peer regeneration
1.5 | Spring 4.2.9 → Spring 6.x | 0 | Slide 5 — Spring & WSService | High | Medium | ArgumentResolver, Security, Springfox
1.6 | View Layer (Jetspeed/Castor/XSL) | 0 | Slide 6 — View Layer | Medium | Low | Castor→dom4j, base class updates
1.7 | JAR Dependencies | 0 | Slide 2 — Stack Overview | Medium | Medium | Classification + upgrade/replace
1.8 | Build System (Ant → Maven) | 0 | Slide 2 — Stack Overview | Medium | One-time | Phase 0 prerequisite
| LAYER 1 TOTAL | 0
2 | Layer 2 — Module-Level Migration
2.x | (To be detailed — see Layer 2 sheet) | 0 | Module-specific |  |  | Functional validation per business module
| LAYER 2 TOTAL | 0
3 | Layer 3 — Integration & Build
3.x | (To be detailed — see Layer 3 sheet) | 0 |  |  |  | Cross-module, multi-country, deployment
| LAYER 3 TOTAL | 0
| GRAND TOTAL (Dev Mandays) | 0 |  |  |  | Scope: until Build. Testing/buffer by senior management.

## Layer 1
Layer 1 — Core Platform Migration (Development Mandays)
Maps to PPT: Stack Migration — Component Risk Map and subsequent detail slides
S.No | Component | Task | Description | Mandays (Dev) | Owner | Assumptions / Notes
1. Java 8 → Java 17 + javax.* → jakarta.* Namespace Migration [PPT: Slide 2]
1 | Java / Jakarta EE | javax.servlet → jakarta.servlet migration | Update all javax.servlet imports to jakarta.servlet across GEB source code. Includes HttpServletRequest, HttpServletResponse, ServletContext, Filter interfaces. |  |  | Scope depends on file count. Can be partially automated via OpenRewrite after Maven conversion.
2 | Java / Jakarta EE | javax.validation → jakarta.validation | Update Bean Validation API imports. Includes @Valid, @NotNull, custom constraint validators. |  |  | Lower volume than servlet — used primarily in Spring controllers.
3 | Java / Jakarta EE | javax.annotation → jakarta.annotation | Update @PostConstruct, @Resource annotations. NOTE: javax.annotation.Generated stays as-is (Java SE). |  |  | Careful: not all javax.annotation classes migrate — only EE-specific ones.
4 | Java / Jakarta EE | Java 8 → 17 API compatibility fixes | Fix any Java 8 specific API usage deprecated/removed in Java 17. Includes removed packages, reflection access restrictions. |  |  | Minimal expected — most Java 8 code runs on 17. Strong encapsulation may affect reflection-heavy code.
5 | Java / Jakarta EE | JDK 17 compilation and runtime testing | Compile full GEB source against JDK 17, resolve compilation errors, verify runtime behaviour. |  |  | Iterative process — compile, fix, recompile.
Java + Jakarta Namespace Subtotal |  |  |  | 0
2. JBoss EAP 7.3 → EAP 8 (Server Runtime) [PPT: Slide 2]
10 | JBoss EAP | EAP 8 server configuration | Configure EAP 8 standalone/domain mode. Update datasource, connection pool, JMS, logging, security subsystem configs. |  |  | Reference existing EAP 7.3 standalone.xml.
11 | JBoss EAP | Deployment descriptor updates | Update web.xml, jboss-web.xml, jboss-deployment-structure.xml for EAP 8 namespace and module structure. |  |  | Finite set of files.
12 | JBoss EAP | EAP 8 deployment and startup validation | Deploy GEB WAR/EAR on EAP 8, resolve classloading issues, validate startup, verify JNDI and datasource connectivity. |  |  | Iterative — deploy, debug, fix, redeploy.
JBoss EAP Subtotal |  |  |  | 0
3. Turbine 2.3.3 → Turbine 7.0 (Framework) [PPT: Slide 3]
20 | Turbine | RunData → PipelineData migration | Add PipelineData parameter and RunData cast to every Action, Layout, and Portlet class. Business logic after cast unchanged. |  |  | High volume, low complexity per file. One cast line per class.
21 | Turbine | Abstract classes → Interfaces adaptation | Action and Layout changed from abstract classes to interfaces. Inherited helper methods removed — must be sourced independently. |  |  | 200+ classes need method signature changes.
22 | Turbine | YAAFI container setup + 3 XML configs | Create containerConfiguration.xml, roleConfiguration.xml, componentConfiguration.xml for Fulcrum/YAAFI. |  |  | One-time config creation. Reference Turbine 7 documentation.
23 | Turbine | pipeline.xml creation + GTPExecuteValve | Create pipeline.xml defining request flow as valves. Write custom GTPExecuteValve (GEB skips Turbine Page mechanism). |  |  | One config file + one custom valve class.
24 | Turbine | Service re-registration (17 banking + 10 platform) | Re-register 27 GEB services in new dual-container model. Config path changes — service code largely unchanged. |  |  | 33 services total. 6 core Turbine services auto-handled.
25 | Turbine | GTPRunDataService adaptation | Adapt custom RunDataService for Turbine 7 container lifecycle. Pool assembly of RunData + Parser + CookieParser. |  |  | POC validated this works. Production version needs full context fields.
26 | Turbine | turbine.properties → new config structure | Migrate turbine.properties entries to appropriate Turbine 7 config files. Some properties move to YAAFI configs. |  |  | Reference POC config as baseline.
27 | Turbine | Daemon and scheduler migration | Verify DaemonFactory, GTPSchedulerService, and all daemon configurations work with Turbine 7 lifecycle. |  |  | Daemons are critical for batch processing — FileToGTPInterfaceDaemon, CEWBulkProcessingDaemon etc.
Turbine Subtotal |  |  |  | 0
4. Torque 3.1.1 → Torque 5.1+ (ORM / Data Layer) [PPT: Slide 4]
30 | Torque | Criteria.add() → Criteria.where() migration | Update every ORM query using Criteria.add() to use Criteria.where(). Same logic, same SQL output, method renamed. |  |  | Mechanical find-and-update. Volume to be confirmed from codebase scan.
31 | Torque | Village library removal (9 files) | Rewrite 9 files that directly import com.workingdogs.village (Record, Value). Replace with Torque 5 native API or direct ResultSet. |  |  | 9 files identified. Each needs individual analysis and rewrite.
32 | Torque | Peer class regeneration from schema.xml | Regenerate all Torque Peer classes using Torque 5.1 generator against schema.xml. |  |  | Requires schema.xml — location under verification (Gokul searching).
33 | Torque | Torque bootstrap via YAAFI | Replace GTPComponentService (removed in Turbine 7) with YAAFI-based Torque initialisation. |  |  | Configuration change — reference POC YAAFI setup.
34 | Torque | Torque 5.1 ORM validation on core tables | Execute actual Criteria queries on GTPCompany, User, Role, Permission, Transaction tables. Verify CRUD operations. |  |  | Core authorization tables — must validate before any module testing.
35 | Torque | Manager/cache layer validation | Verify AbstractBaseManager and caching layer works with Torque 5.x. Permission caching critical for performance. |  |  | Under verification — Torque 5 redesigned manager layer.
Torque Subtotal |  |  |  | 0
5. Spring 4.2.9 → Spring 6.x + WSService (REST Layer) [PPT: Slide 5]
40 | Spring | CustomControllerArgumentResolver rewrite | Rewrite the class that bridges Spring MVC and Turbine. Interface changes from javax.servlet to jakarta.servlet. Every controller depends on this. |  |  | Strategic fix point. Single class but high impact — must be done first.
41 | Spring | Spring controller javax→jakarta migration | Update all javax.servlet imports in Spring controllers to jakarta.servlet. Update ContextUtils.createRundata() calls. |  |  | Per-controller work. Volume depends on controller count.
42 | Spring | Springfox → springdoc-openapi replacement | Replace all Springfox annotations: @Api→@Tag, @ApiOperation→@Operation, @ApiParam→@Parameter. Configure springdoc. |  |  | Mechanical annotation changes. No business logic impact.
43 | Spring | Spring Security 6 reconfiguration | Rewrite FilterChainProxy configuration. Spring Security 6 filter chain API is completely different from 4.x. |  |  | Security-critical — must be tested thoroughly.
44 | Spring | webservice-servlet.xml update | Update Spring dispatcher config for Spring 6 namespace, bean definitions, argument resolvers, validation config. |  |  | Single config file — but central to all WSService routing.
45 | Spring | javax.validation → jakarta.validation | Update validation annotations and custom validators used in Spring controllers for GTP_PARAM_DATA interaction. |  |  | May overlap with Java/Jakarta task — avoid double counting.
46 | Spring | Spring 6 JAR set replacement (~22 JARs) | Replace entire Spring 4.x JAR set with Spring 6.x equivalents. No partial upgrade possible. |  |  | spring-core, spring-web, spring-webmvc, spring-security, etc.
47 | Spring | Spring 6 integration testing | Validate all WSService REST endpoints function correctly. Test IDB→GEB request flow end-to-end. |  |  | Requires IDB test environment connectivity.
Spring Subtotal |  |  |  | 0
6. View Layer (Jetspeed / Castor / XSL / ECS) [PPT: Slide 6]
50 | View Layer | Castor XML → dom4j parser replacement | Replace Castor XML parser for PSML files with dom4j. Castor uses reflection blocked by Java 17 strong encapsulation. |  |  | Page definitions unchanged — only parser replacement.
51 | View Layer | Base class chain migration (4 classes) | Update ActionPortlet → GTPRootPortlet → AbstractPortlet → Portlet chain for Turbine 7 interface changes. |  |  | 4 base classes. Changes cascade to all portlets via inheritance.
52 | View Layer | Deprecated method resolution in base chain | Identify and resolve deprecated methods and interface changes at each level of the portlet base chain. |  |  | Careful analysis required — affects all portlets.
53 | View Layer | Xalan 2.7.2 → 2.7.3 upgrade | Security patch for CVE-2022-34169. No API change. Verify all XSL stylesheets render correctly. |  |  | Drop-in JAR replacement + XSL regression validation.
54 | View Layer | PSML file validation | Verify all PSML page definitions parse correctly with new dom4j parser. Validate portlet placement on pages. |  |  | Functional validation — all portal pages must render correctly.
55 | View Layer | Velocity template validation | Verify TopBIBP.vm, BottomBIBP.vm, and other Velocity templates serve correctly on Turbine 7. |  |  | Already confirmed Java 17 compatible — validation only.
View Layer Subtotal |  |  |  | 0
7. JAR Dependencies (Classification + Migration) [PPT: Slide 2]
60 | JARs | JAR javax classification (Jakarta EE vs Java SE) | Classify all JARs: which use Jakarta EE javax (must change) vs Java SE javax (safe). Extract and scan .class files. |  |  | Critical first activity — determines true migration scope.
61 | JARs | JAR upgrade — Jakarta EE compatible versions | For JARs with Jakarta EE javax: find and replace with Jakarta-compatible versions from Maven Central. |  |  | Most open-source JARs have Jakarta versions available (e.g., ESAPI 2.7.0).
62 | JARs | Finastra internal JAR recompilation | Locate source for Finastra internal JARs. Recompile against Java 17 + Jakarta EE. |  |  | Requires source access from Finastra. Vendor engagement dependency.
63 | JARs | UOB/Bank internal JAR recompilation | Locate source for UOB-customised JARs. Recompile against target stack. |  |  | Source should be available within bank.
64 | JARs | log4j 1.x → log4j2 migration | Replace log4j 1.2.17 (active CVE) with log4j2. Update log4j configuration and API calls. |  |  | Security-critical — should be addressed independent of migration timeline.
65 | JARs | JAR compatibility testing | Test all replaced/upgraded JARs in integrated environment. Verify no runtime ClassNotFoundException or NoSuchMethodError. |  |  | Iterative — test, fix, retest.
JAR Dependencies Subtotal |  |  |  | 0
8. Build System (Ant → Maven) [PPT: Slide 2]
70 | Build | Ant → Maven project structure conversion | Convert GEB build from Apache Ant (build.xml) to Maven (pom.xml). Define module structure, dependencies, profiles. |  |  | Phase 0 prerequisite. OpenRewrite javax→jakarta automation requires Maven.
71 | Build | Maven dependency management | Define all GEB dependencies in pom.xml with correct Jakarta EE compatible versions. |  |  | Replaces manual JAR management in WEB-INF/lib.
72 | Build | CI/CD pipeline update (Jenkins) | Update Jenkins build pipeline for Maven. Configure build profiles for target environment. |  |  | Jenkins stays — only build command changes from Ant to Maven.
73 | Build | WAR/EAR packaging for EAP 8 | Configure Maven build to produce correct WAR/EAR packaging for JBoss EAP 8 deployment. |  |  | Deployment descriptor structure may differ from EAP 7.3.
Build System Subtotal |  |  |  | 0
LAYER 1 — CORE PLATFORM MIGRATION TOTAL |  |  |  | 0

## Layer 2
Layer 2 — Module-Level Migration & Functional Validation (Development Mandays)
Each business module requires developer-level migration validation — not just compilation, but end-to-end functional flow
THIS IS WHERE 2 YEARS OF GEB PRODUCTION KNOWLEDGE IS REQUIRED — module flows, country variations, daemon behaviour, external integrations
S.No | Module | Task | Description / Scope | Mandays (Dev) | Owner | Assumptions / Dependencies
1. Fund Transfer (TT / CBPR+)
Complexity: Complex — multi-step approval, bulk processing, CEW→DMP→GEB flow, status callbacks, 6-country variations
1.1 | Fund Transfer | Portlet-specific code migration (screens, actions)
1.2 | Fund Transfer | Bulk file upload flow validation (IDB→CEW→DMP→GEB→CEW callback)
1.3 | Fund Transfer | CEWBulkProcessingDaemon validation
1.4 | Fund Transfer | DMP interface validation (SE_HFile processing)
1.5 | Fund Transfer | Status callback to CEW validation
1.6 | Fund Transfer | Country-specific TT configuration (SG, MY, VN, CN, HK, TH)
1.7 | Fund Transfer | ROS/Core Banking ACK callback validation
Fund Transfer Subtotal |  |  |  | 0
2. Fund Transfer (BAU / Payroll)
Complexity: Complex — different daemon, no CEW interaction, DMP S-File flow
2.1 | Fund Transfer | Portlet-specific code migration
2.2 | Fund Transfer | FileToGTPInterfaceDaemon validation
2.3 | Fund Transfer | BAU flow: IDB→GEB→DMP(S-File)→GEB(SE_HFile) validation
2.4 | Fund Transfer | prod_status_code handling validation
2.5 | Fund Transfer | Country-specific BAU configuration
Fund Transfer Subtotal |  |  |  | 0
3. Account Statement
Complexity: Complex — batch processing, core banking integration, Torque-heavy
3.1 | Account Statement | Portlet-specific code migration
3.2 | Account Statement | Account Statement batch daemon validation
3.3 | Account Statement | Core banking data import/export validation
3.4 | Account Statement | Torque-based object lifecycle (header→lines→transactions)
3.5 | Account Statement | Unicode/encoding handling (0x1A character issue previously found)
3.6 | Account Statement | Country-specific statement formats
Account Statement Subtotal |  |  |  | 0
4. Letter of Credit (LC)
Complexity: Complex — trade finance, EAI integration, multi-country
4.1 | Letter of Credit | Portlet-specific code migration
4.2 | Letter of Credit | LC creation/amendment/advising flow validation
4.3 | Letter of Credit | EAI integration validation
4.4 | Letter of Credit | Country-specific LC configuration
4.5 | Letter of Credit | XSL template rendering validation
Letter of Credit Subtotal |  |  |  | 0
5. Bank Guarantee (BG)
Complexity: Medium-Complex — trade finance
5.1 | Bank Guarantee | Portlet-specific code migration
5.2 | Bank Guarantee | BG issuance/amendment flow validation
5.3 | Bank Guarantee | EAI integration validation
5.4 | Bank Guarantee | Country-specific BG configuration
Bank Guarantee Subtotal |  |  |  | 0
6. Trust Receipt
Complexity: Medium — trade finance
6.1 | Trust Receipt | Portlet-specific code migration
6.2 | Trust Receipt | Trust Receipt flow validation
6.3 | Trust Receipt | Integration with LC/BG modules
Trust Receipt Subtotal |  |  |  | 0
7. Organization Module (User/Role/Permission)
Complexity: Critical — Torque-heavy, caching, authorization model
7.1 | Organization Module | Portlet-specific code migration
7.2 | Organization Module | User/Company/Role/Permission CRUD validation
7.3 | Organization Module | Torque Manager caching validation (permission cache)
7.4 | Organization Module | ACL (Access Control List) validation
7.5 | Organization Module | Menu visibility based on role
7.6 | Organization Module | Table-level access permission validation
7.7 | Organization Module | Multi-country role configuration
Organization Module Subtotal |  |  |  | 0
8. Interops
Complexity: Medium — external file processing
8.1 | Interops | Portlet-specific code migration
8.2 | Interops | Interops file upload/download flow validation
8.3 | Interops | GEB↔DMP interaction validation
8.4 | Interops | IDB display validation
Interops Subtotal |  |  |  | 0
9. Trade Middle Office
Complexity: Medium — reporting and monitoring
9.1 | Trade Middle Office | Portlet-specific code migration
9.2 | Trade Middle Office | Middle office screen validation
9.3 | Trade Middle Office | Report generation validation
Trade Middle Office Subtotal |  |  |  | 0
10. Bank Administration
Complexity: Medium — system configuration
10.1 | Bank Administration | Portlet-specific code migration
10.2 | Bank Administration | Admin configuration screens validation
10.3 | Bank Administration | System parameter management
10.4 | Bank Administration | Country/branch configuration validation
Bank Administration Subtotal |  |  |  | 0
LAYER 2 — MODULE-LEVEL MIGRATION TOTAL |  |  |  | 0

## Layer 3
Layer 3 — Integration, Multi-Country & Build Validation (Development Mandays)
S.No | Component | Task | Description | Mandays (Dev) | Owner | Assumptions / Notes
1 | Integration | Cross-module flow validation | Validate flows that span multiple modules — e.g., Bulk File Upload touches FT, DMP, CEW, and IDB |  |  | Requires all individual modules to be migrated first
2 | Integration | EAI connectivity validation | Verify GEB→EAI integration works on new stack. Message formats, connection parameters, error handling. |  |  | EAI system unchanged — GEB side needs validation
3 | Integration | DMP interface validation | Verify all DMP↔GEB interfaces — S-File, SE_HFile, prod_status_code handling, rejection flows. |  |  | Critical — known production issues in this interface
4 | Integration | IDB↔WSService endpoint validation | Verify all IDB→GEB REST API calls work end-to-end on new stack. |  |  | Depends on Spring 6 migration completion
5 | Integration | ROS/Core Banking callback validation | Verify ACK processing from ROS, status code reconciliation, BK vs FT level status. |  |  | Known fragile area — BK rejection vs FT status mismatch
6 | Multi-Country | Singapore (SG) configuration validation | Validate SG-specific configs, templates, parameters, country-specific flows. |  |  | Primary country — validate first
7 | Multi-Country | Malaysia (MY) configuration validation | Validate MY-specific configs, encoding, templates, regulatory requirements.
8 | Multi-Country | Vietnam (VN) configuration validation | Validate VN-specific configs, encoding (UTF-8 handling critical), templates. |  |  | Encoding issues previously identified
9 | Multi-Country | China (CN) configuration validation | Validate CN-specific configs, encoding, templates.
10 | Multi-Country | Hong Kong (HK) configuration validation | Validate HK-specific configs, templates.
11 | Multi-Country | Thailand (TH) configuration validation | Validate TH-specific configs, encoding, templates.
12 | Build | Full build packaging (WAR/EAR) | Complete Maven build producing deployable WAR/EAR for EAP 8. All dependencies resolved. |  |  | Final packaging after all components migrated
13 | Build | Deployment to SIT environment | Deploy migrated GEB to SIT environment on EAP 8 + JDK 17. Resolve deployment issues. |  |  | SIT environment must be provisioned with target stack
14 | Build | Daemon startup and scheduling validation | Verify all GEB daemons start correctly, scheduling works, no race conditions. |  |  | FileToGTPInterfaceDaemon, CEWBulkProcessingDaemon, Account Statement daemon etc.
15 | Build | Static resource and MIME type validation | Verify all file types (.xsl, .psml, .vm, .properties, etc.) served correctly on EAP 8. |  |  | MIME mappings and static resource servlet config may differ
16 | Build | Smoke test — critical path validation | Execute critical business paths end-to-end: Login → FT creation → Approval → Release → Statement. |  |  | Final developer validation before handoff for formal testing
LAYER 3 — INTEGRATION & BUILD TOTAL |  |  |  | 0

## Assumptions & Risks
Assumptions, Dependencies & Risks
# | Type | Description | Mitigation / Notes
1 | Assumption | Scope: Estimation covers development effort until Build. Unit testing, SIT, UAT, buffer, and project management are handled separately by senior management.
2 | Assumption | Environment: SIT environment with JBoss EAP 8 + JDK 17 will be available for migration validation.
3 | Assumption | Source Access: Full GEB source code access is available. Finastra internal JAR source will be obtained through vendor engagement.
4 | Assumption | POC Baseline: Mini-GEB POC on Turbine 7 / Java 17 / Tomcat 10 serves as the validated baseline for platform migration approach.
5 | Assumption | schema.xml: Torque schema.xml file will be located or reverse-engineered from existing Peer classes and database DDL.
6 | Assumption | No Functional Change: Migration is a platform upgrade only — no business logic changes, no new features, no functional enhancements.
7 | Assumption | JAR Classification: Final JAR migration effort depends on classification outcome. Significant portion expected to be Java SE javax (safe).
8 | Dependency | I-Sprint: Jakarta EE compatible I-Sprint JAR required from vendor. Timeline not in Wipro control. POTENTIAL PROGRAMME BLOCKER.
9 | Dependency | Finastra: Java 17 compatible binaries or source code required from Finastra for internal JARs.
10 | Dependency | Bank: Confirmation needed: expected DMP behaviour when prod_status_code = 01. ROS ACK contract clarification.
11 | Risk | I-Sprint Blocker: If I-Sprint cannot deliver Jakarta EE JAR in time, token authentication will not function on upgraded stack.
12 | Risk | Finastra Source: If Finastra source is unavailable, internal JARs cannot be recompiled. Requires alternative approach or vendor escalation.
13 | Risk | GTPParameterParser: Parser initialisation on Fulcrum container not yet resolved. Under active investigation — may require alternative approach.
14 | Risk | Torque Manager: AbstractBaseManager compatibility with Torque 5.x unconfirmed. Permission caching layer may need rework.
15 | Risk | Country Variations: Country-specific configurations (especially encoding for VN, CN, TH) may surface issues only during multi-country testing.