## Executive_Summary
OpenRewrite migration matrix — summary for review
Source references: C:\openRewrite (rewrite.yml, *-CONSTRAINTS.md, rewrite-*.yml). Automation = recipe can apply changes; Partial = review/tests required; Manual = backlog / not covered by recipes in this workspace.
Category | Migration scope | Primary automated recipes (workspace / upstream) | Automation coverage (high-level) | Manual / backlog (high-level) | Typical risk | Key reference files under C:\openRewrite
Java EE → Jakarta EE | javax.* → jakarta.* (selected enterprise APIs) | com.uob.openrewrite.JavaxToJakartaNamespaces; org.openrewrite.java.migrate.jakarta.JavaxMigrationToJakarta | High for Java sources; partial for XML/descriptors | Non-Java resources, third-party JARs still on javax.*, server config | Medium — compile + integration test | rewrite.yml; OPENREWRITE-LEGACY-TO-JAKARTAEE-JDK17.md
Torque 3.x → Torque 7.x | ORM + WAR integration | com.uob.openrewrite.Torque3To7WithJakartaWebTier; Torque3To7OptionalNewCriteriaPackage (opt-in risky); Torque3To7ManualBacklog | Low–medium (Jakarta web tier + optional Criteria rename); generator/schema not automated | Village removal, peer regeneration, schema XSD, semantic Criteria, build coordinates | High without regenerated peers and DB tests | rewrite-torque3-to-7-webapp.yml; OPENREWRITE-TORQUE3-TO-7-RECIPE-AND-CONSTRAINTS.md; TORQUE-3-TO-7-UPGRADE-SUMMARY.md
Turbine 3.x / 4.x → Turbine 7.x | Portal servlet pipeline + Fulcrum | com.uob.openrewrite.Turbine4To7WebCompatible; Turbine4To7ManualBacklog; (template) com.misys.rewrite.Turbine3To7PackageUpgrade | Medium for deterministic Java/Jakarta; valves/bootstrap not fully automated | AbstractValve→Valve, Turbine subclass, pipeline XML, Log4j2, dependencies, JSP | High for custom valves and framework forks | rewrite-turbine4-to-7-webapp.yml; OPENREWRITE-TURBINE4-TO-7-RECIPE-AND-CONSTRAINTS.md; misys-openrewrite-template\rewrite\
Spring Framework 4.x → 7.x | Spring 6 (Jakarta) then Spring 7 | Phase A: com.uob.openrewrite.SpringFramework4xTo6xJakarta (+ optional WithSpringSecurity6). Phase B (upstream): org.openrewrite.java.spring.framework.UpgradeSpringFramework_7_0 | High for many Spring API + POM changes; partial for XML/Security/OAuth | JDK 17+, Hibernate 3/4 removal, JSP/JSTL, XML config, third-party starters, Spring Security semantics | High — multi-phase program | rewrite-spring-4-to-6-jakarta.yml; OPENREWRITE-SPRING4-TO-6-RECIPE-AND-CONSTRAINTS.md
Cross-cutting | JDK / build / CI | rewrite-migrate-java (Java version recipes — see LEGACY doc); not all wired in this pom | Varies by recipe | Toolchain, Docker, vendor libs, performance/regression | Medium | OPENREWRITE-LEGACY-TO-JAKARTAEE-JDK17.md; pom.xml (plugin + recipe classpath)
Estimation columns for management:
Add portfolio-specific columns (e.g. FTE weeks, cost, priority) to detail sheets or duplicate this sheet.

## JavaEE_to_JakartaEE
JavaEE_to_JakartaEE
Recipes from C:\openRewrite\rewrite.yml — javax → jakarta for common enterprise APIs in Java sources.
SECTION A — Automated / semi-automated recipes
Recipe display name | Recipe FQN | Automation level | Applies to | Notes / upstream
Migrate javax namespaces to jakarta (selected enterprise APIs) | com.uob.openrewrite.JavaxToJakartaNamespaces | Full (Java) | Application Java sources in configured modules | Composite: JavaxMigrationToJakarta + explicit ChangePackage rules
Jakarta migration (broad) | org.openrewrite.java.migrate.jakarta.JavaxMigrationToJakarta | Full (Java, broad) | Same | Included inside JavaxToJakartaNamespaces
Explicit servlet migration | org.openrewrite.java.ChangePackage javax.servlet → jakarta.servlet | Full | Java | Part of JavaxToJakartaNamespaces
Explicit JPA migration | org.openrewrite.java.ChangePackage javax.persistence → jakarta.persistence | Full | Java | Part of JavaxToJakartaNamespaces
Explicit Bean Validation | org.openrewrite.java.ChangePackage javax.validation → jakarta.validation | Full | Java | Part of JavaxToJakartaNamespaces
SECTION B — Manual backlog (not fully automatable)
ID | Backlog area | Why manual / partial | Suggested owner
J-01 | JSP / taglibs / Facelets | JSP not covered by default Java-only recipes; taglib URIs must match Jakarta impl | Web + build
J-02 | web.xml / glassfish-web.xml / deployment descriptors | Schema version, metadata-complete, vendor XML | App server + integration
J-03 | Third-party dependencies | Libraries still exposing javax.* APIs must be upgraded | Platform / architecture
J-04 | Non-Java config (properties, YAML) | May need targeted recipes or manual edits | DevOps / dev
J-05 | Generated / vendor sources | Excluded or overwritten by codegen; align generator first | Build
J-06 | Behavioral API changes | Some jakarta APIs differ subtly; integration tests required | QA + dev
SECTION C — Estimation / sign-off (fill for senior management review)
Backlog item / work package | Owner role | Estimate (days) | Confidence | Dependencies | Status | Reviewer sign-off

## Torque3_to_Torque7
Torque3_to_Torque7
Torque ORM 3.x → 7.x per OPENREWRITE-TORQUE3-TO-7-RECIPE-AND-CONSTRAINTS.md and Apache migration guide.
SECTION A — Automated / semi-automated recipes
Recipe display name | Recipe FQN | Automation level | Type | Notes
Torque-era web — Jakarta web tier | com.uob.openrewrite.Torque3To7WithJakartaWebTier | Full (delegates to Jakarta recipe) | Transform | Does not regen Torque peers or remove Village
OPTIONAL RISKY: util.Criteria → criteria.Criteria | com.uob.openrewrite.Torque3To7OptionalNewCriteriaPackage | Partial / risky | Transform | Semantic differences per Apache docs — opt-in only
Torque manual backlog detection | com.uob.openrewrite.Torque3To7ManualBacklog | N/A (detection) | Backlog generator | FindTypes + text Find; exportDatatables
SECTION B — Manual backlog (not fully automatable)
ID | Backlog area | Description | Suggested owner
TQ-01 | Village removal | Torque 7 runtime does not use Village; redesign data access | Backend lead
TQ-02 | Code generation | Schema XSD, Maven Torque plugin, templates, regen peers/OM/MapBuilder | Build + DBA
TQ-03 | Criteria semantics | OR/AND, CUSTOM, doDelete table resolution when moving to criteria.Criteria | Backend dev
TQ-04 | null Connection audit | Torque 4+ errors on null connection where Torque 3 tolerated | Backend dev
TQ-05 | Torque.properties / datasource XML | Framework integration (e.g. Turbine component) | Platform
TQ-06 | JDBC / DB scripts | Dialect-specific scripts if not MySQL-only | DBA
SECTION C — Estimation / sign-off (fill for senior management review)
Backlog item / work package | Owner role | Estimate (days) | Confidence | Dependencies | Status | Reviewer sign-off

## Turbine_to_Turbine7
Turbine_to_Turbine7
Turbine 3.x/4.x → 7.x: C:\openRewrite recipes + optional misys-openrewrite-template Turbine3To7 safe set.
SECTION A — Automated / semi-automated recipes
Recipe display name | Recipe FQN | Automation level | Location | Notes
Turbine 4→7 web compatible | com.uob.openrewrite.Turbine4To7WebCompatible | Medium | rewrite.yml | Jakarta + TemplateInfo ChangeType + format
Turbine manual backlog | com.uob.openrewrite.Turbine4To7ManualBacklog | Detection | rewrite.yml | AbstractValve, Turbine, modules, createRuntimeDirectories Find
Turbine 3→7 package upgrade (safe subset) | com.misys.rewrite.Turbine3To7PackageUpgrade | Medium | misys-openrewrite-template\rewrite\rewrite-turbine7-upgrade.yml | Narrower servlet Jakarta + TemplateInfo; use if aligned with mapping table
Turbine manual backlog (template) | com.misys.rewrite.Turbine3To7ManualBacklog | Detection | misys-openrewrite-template\rewrite\rewrite-turbine7-manual-backlog.yml | Additional FindTypes for services/modules
SECTION B — Manual backlog (not fully automatable)
ID | Backlog area | Description | Suggested owner
TB-01 | Custom pipeline valves | AbstractValve removed in Turbine 7; implement Valve + Jakarta types | Framework dev
TB-02 | Turbine servlet subclass | createRuntimeDirectories vs configureApplication / Path / JAXB | Framework dev
TB-03 | turbine-classic-pipeline.xml | DefaultSetEncodingValve ordering | DevOps + dev
TB-04 | componentConfiguration / roles | Fulcrum component class compatibility | Platform
TB-05 | Logging | Log4j 1.x properties → Log4j2 XML | Ops
TB-06 | Dependencies | turbine + Fulcrum + Torque versions + Servlet 5 container | Architecture
SECTION C — Estimation / sign-off (fill for senior management review)
Backlog item / work package | Owner role | Estimate (days) | Confidence | Dependencies | Status | Reviewer sign-off

## Spring4_to_Spring7
Spring4_to_Spring7
Roadmap: Phase A — Spring 6 + Jakarta (wired in C:\openRewrite). Phase B — Spring 7 (upstream OpenRewrite; requires compatible rewrite-spring version).
SECTION A — Automated / semi-automated recipes
Recipe display name | Recipe FQN | Automation level | Phase | Notes
Spring → 6.0 + Jakarta namespaces | com.uob.openrewrite.SpringFramework4xTo6xJakarta | High (Java + POM) | A — Spring 6 | UpgradeSpringFramework_6_0 + JavaxToJakartaNamespaces
Spring → 6.0 + Jakarta + Spring Security 6 | com.uob.openrewrite.SpringFramework4xTo6xWithSpringSecurity6 | High (partial Security) | A — Spring 6 | Adds UpgradeSpringSecurity_6_0
Spring 4→6 manual backlog detection | com.uob.openrewrite.SpringFramework4To6ManualBacklog | Detection | A — Spring 6 | Legacy MVC/JDBC/Hibernate3-4, javax in XML/JSP
Migrate to Spring Framework 7.0 (upstream) | org.openrewrite.java.spring.framework.UpgradeSpringFramework_7_0 | High (with caveats) | B — Spring 7 | Run after 6.x stable; may require newer rewrite-spring than pinned in pom; includes e.g. JUnit/Jackson upgrades per OpenRewrite docs
Migrate to Spring Security 7.0 (upstream) | org.openrewrite.java.spring.security7.UpgradeSpringSecurity_7_0 | Partial | B — Spring 7 | If applicable; coordinate with Spring Framework 7 / Boot 4 stack
SECTION B — Manual backlog (not fully automatable)
ID | Backlog area | Description | Suggested owner
SP-01 | JDK 17+ | Spring 6+ baseline; CI and runtime images | Platform
SP-02 | Servlet 5+ container | Tomcat 10+ / Jetty 11+ / EE9+ for WARs | Ops
SP-03 | Hibernate 3/4 Spring support | Removed in Spring 6; migrate ORM stack | Architecture
SP-04 | SimpleJdbcTemplate / WebMvcConfigurerAdapter | Removed/deprecated patterns; refactor | Backend dev
SP-05 | Spring XML / jee: namespace | Bean definitions and JNDI | Backend dev
SP-06 | JSP/JSTL Jakarta | View layer alignment | Web dev
SP-07 | OAuth2 / SAML / custom security | Beyond recipe defaults | Security architect
SP-08 | Third-party Spring starters | Camel, CXF, vendor — Jakarta-compatible versions | Architecture
SP-09 | Spring 7 follow-on | Validate rewrite-spring version; run UpgradeSpringFramework_7_0 separately | Tech lead
SECTION C — Estimation / sign-off (fill for senior management review)
Backlog item / work package | Owner role | Estimate (days) | Confidence | Dependencies | Status | Reviewer sign-off