## Slide 1
UOB
WIPRO CONSULTING
GEB FCC Platform
JBoss EAP 8 Migration Assessment
Finastra Fusion Corporate Channel (BIB Plus)
Turbine 2.3.3 → Turbine 7 | Java 8 → Java 17 | JBoss EAP 7 → EAP 8 | Jakarta EE
138
JARs Assessed
33
Services Mapped
16
Breaking API Changes
5
Architecture Layers
Presented to: UOB Bank Singapore | Date: April 2026 | Classification: Confidential
Wipro Consulting | Digital Engineering Practice | Singapore

## Slide 2
Agenda
What we will walk through today
GEB FCC Platform — JBoss EAP 8 Migration Assessment | Wipro Consulting × UOB Bank Singapore | Confidential
01
Platform Overview
GEB FCC — what it is, why it matters, current tech stack
02
Assessment Methodology
War room sprint, source code analysis, hands-on POC
03
GEB Architecture Deep Dive
5-layer service model, 33 services fully mapped
04
Turbine 7 Migration Analysis
API changes proven by compilation — not theoretical
05
RunData Architecture Risk
The central data bus and its migration impact
06
POC — Mini-GEB Live on Turbine 7
4 architecture tests — what passed, what failed, why
07
Risk & Impact Matrix
138 JARs, 16 breaking changes, severity classification
08
Recommendations & Next Steps
Migration path, effort, timelines

## Slide 3
GEB FCC Platform Overview
Finastra Fusion Corporate Channel — Current State
GEB FCC Platform — JBoss EAP 8 Migration Assessment | Wipro Consulting × UOB Bank Singapore | Confidential
WHAT IS GEB FCC?
Finastra Fusion Corporate Channel
Banking portal (BIB Plus) — UOB's primary corporate internet banking platform
Serving
UOB corporate customers across Singapore, Malaysia, Vietnam, China, Hong Kong, Thailand
Business Scope
Fund Transfer, Letter of Credit, Bank Guarantee, Trade Finance, Payments
Users
Corporate MAKER / CHECKER / ADMIN roles with ACL-enforced access
Current Stack
JBoss EAP 7.x · Java 8 · Apache Turbine 2.3.3 (Finastra-customised)
Target Stack
JBoss EAP 8 · Java 17 · Jakarta EE · Turbine 7 · Tomcat 10 compatible
CURRENT TECHNOLOGY STACK
Runtime
JBoss EAP 7.x
Java
Java 8 (EOL)
Framework
Apache Turbine 2.3.3 (Finastra bundle)
Servlet API
javax.servlet.* namespace
Template Engine
Velocity 1.7 + ECS 1.4.2
XSLT Processor
Xalan 2.7.2
ORM
Torque 3.1.1 + PoolBrokerService
Portal Pages
PSML via Castor XML
Logging
log4j 1.2.17 (CRITICAL CVE)
Build
Apache Ant + Bitbucket + Jenkins
Database
Oracle + DBCP connection pool

## Slide 4
Assessment Methodology
How we approached this — War Room Sprint with hands-on validation
GEB FCC Platform — JBoss EAP 8 Migration Assessment | Wipro Consulting × UOB Bank Singapore | Confidential
01
Source Code Analysis
Eclipse IDE deep-dive on real GEB source
Confirmed: DefaultGTPLayout extends Layout (not VelocityLayout)
Confirmed: GTPRootPortlet.addGridComparator() — data.getPage() pattern
Confirmed: 5-layer service architecture from turbine.properties (796 lines)
Confirmed: 33 services fully class-mapped across 5 layers
02
JAR Compatibility Mapping
138 production JARs assessed individually
CVE scoring, Java 17 compatibility, Jakarta EE readiness
33 CRITICAL · 52 Upgrade needed · 28 Internal rebuild · 12 Verify
Identified devtools.jar + SNAPSHOT JARs in production
log4j 1.2.17 flagged as CRITICAL CVE — immediate action required
03
War Room Sprint
Dedicated war room with offshore team (6 engineers)
Gokul — Torque + Bank Admin assessment
Sakthi — Trade Core + javax→jakarta namespace scan
Akshith/Chandra — Utilities, Spring layer, XSL layer
Kreshan/Archana — Token mechanism + E2EEService (grey area)
04
Hands-On POC — Mini-GEB
Built mini-replica of ACTUAL GEB architecture from scratch
Ran on Turbine 7 + Java 17 + Jakarta EE + Tomcat 10
Replicated: RunData pooling, PSML, ECS→XSL, PoolBroker, Velocity
4 RunData architecture tests — executed live, results verified
Every finding traceable to specific GEB source class

## Slide 5
GEB FCC Platform — JBoss EAP 8 Migration Assessment | Wipro Consulting × UOB Bank Singapore | Confidential
GEB Architecture — 5-Layer Turbine Service Model
Fully mapped from turbine.properties + portal.properties + services.xml + deep Eclipse source analysis
LAYER 5
Disabled Services
IntakeService
MimeTypeService
PythonScreenFactory
Commented out — dead code
LAYER 4
17 GTP Business Services
GTPPoolBrokerService
GTPAuthenticationService
GTPAuthorizationService
E2EEService
PsmlScreenManager
DaemonFactory
+11 more
portal.properties / services.xml — NOT in turbine.properties
LAYER 3
Pure GTP Services
GTPAuditService
GTPDefaultTemplateEngineService
No Apache equivalent
LAYER 2
Apache Services — Overridden by Finastra GTP
GTPRunDataService
EHCacheService
GTPSchedulerService
XSLTCachingService
UniqueSessionService
PortalUploadService
AdapterForTurbineSecurityService
Apache class bypassed — GTP class active
LAYER 1
Apache Standard Services (Backbone)
TurbineFactoryService
TurbinePoolService
TurbineVelocityService
TurbineTemplateService
TurbineAssemblerBrokerService
TurbinePullService
Proven mandatory — crash if removed (POC validated)

## Slide 6
RunData — The Central Data Bus
Every Action, Portlet and Layout receives this single object — migration impact is widest here
GEB FCC Platform — JBoss EAP 8 Migration Assessment | Wipro Consulting × UOB Bank Singapore | Confidential
WHAT RUNDATA CARRIES — confirmed from Eclipse debugger
DefaultTurbineRunData base
HttpServletRequest, Response, Session, ParameterParser, CookieParser
GTPRunData additions
getMiniGEBUser() · getCompanyAcl() · getUserAcl()
Country Code
getCountryCode() — drives GTP_PARAM_DATA lookup (SG/MY/VN/CN/HK/TH)
Token / SSO State
isTokenAuthenticated() · isSsoAuthenticated()
Pool Context
cfg[0]=DefaultGTPRunData cfg[1]=GTPParameterParser cfg[2]=DefaultCookieParser
Assembler
GTPRunDataService.getRunData() assembles all 3 from TurbinePoolService
Recycle
putRunData() recycles all 3 separately — session isolation critical for banking security
MIGRATION IMPACT — proven by POC (not theoretical)
CRITICAL
data.getPage() REMOVED from RunData in Turbine 7
GTPRootPortlet.addGridComparator() uses data.getPage().getBody().addElement(script) — ALL portlets break. 10+ compile errors proven.
CRITICAL
Action / Layout changed from class → interface
Every extends Action / extends Layout in GEB = compile error. Affects all 18+ business modules.
HIGH
GTPParameterParser integration broken
fulcrum-parser 4.0.0 does not support custom parser registration. XSS sanitization, Dojo indexed params silently bypassed. Proven in POC — Test 2 FAIL.
HIGH
javax.servlet.* → jakarta.servlet.* namespace
fulcrum-parser 2.0.1 crashes on Tomcat 10. ALL libraries compiled against javax.* will fail. Proven by ClassNotFoundException.
HIGH
TurbinePoolService / TurbineFactoryService removed
Both services removed from Turbine 7. Any turbine.properties entry referencing them = ClassNotFoundException on startup.
MEDIUM
RunData → PipelineData signature changes
Every doPerform(RunData) in Actions must change to doPerform(PipelineData). Silent data bleed risk if recycle() not updated.

## Slide 7
GEB FCC Platform — JBoss EAP 8 Migration Assessment | Wipro Consulting × UOB Bank Singapore | Confidential
POC — Mini-GEB Running Live on Turbine 7 + Java 17
We built a mini-replica of the ACTUAL GEB application — same architecture, same patterns — and validated it on Turbine 7 + Java 17 + Jakarta EE. Note: Tomcat 10 used for POC validation; production target remains JBoss EAP 8.
TEST 1
✓
PASS
Custom RunDataService Creates Our RunData Class
MiniGEBRunDataService successfully creates DefaultMiniGEBRunData (our custom class) in Turbine 7. Registered via turbine.properties.
Log: DefaultMiniGEBRunData CREATED: RunData-2eb84678 (class=DefaultMiniGEBRunData)
TEST 2
✗
FAIL
Custom ParameterParser Cannot Be Plugged In
GTPParameterParser equivalent cannot be registered in Turbine 7's fulcrum-parser 4.0.0 layer. XSS sanitization, Dojo indexed params silently bypassed.
Error: fulcrum-parser 4.0.0 DefaultParserService does not support custom parser class
TEST 3
✓
PASS
Custom Fields Flow Correctly Through Entire Pipeline
getMiniGEBUser(), getCompanyAcl(), getCountryCode() all correctly populated and accessible in Action → Portlet → Layout chain.
Browser: pavan.demo | MAKER_CHECKER | SG | 6 ACL permissions loaded
TEST 4
✓
PASS
Pool Recycling Works — Same Object Reused
TurbinePoolService returns same RunData object across requests. recycle() clears all GEB fields. recycleCount increments per request.
Log: RECYCLED RunData-77bd8218 recycleCount=1, 2, 3 — same ID across all requests

## Slide 8
POC Architecture — What Mini-GEB Replicated
Each component mirrors its real GEB counterpart exactly
GEB FCC Platform — JBoss EAP 8 Migration Assessment | Wipro Consulting × UOB Bank Singapore | Confidential
HTTP Request
Browser (Dojo)
Turbine Servlet
org.apache.turbine.Turbine
MiniGEBRunDataService
Mirrors GTPRunDataService
Custom Pipeline Valve
Mirrors ClassicPipeline
DefaultMiniGEBLayout
implements Layout (confirmed)
PSMLManager (dom4j)
Replaces Castor XML
EntityListPortlet
ECS → Xalan → HTML
MySQL Response
8 entities loaded live
Layout
PROVEN
REAL GEB
DefaultGTPLayout extends Layout
(NOT VelocityLayout — confirmed from Eclipse Image 4)
MINI-GEB
DefaultMiniGEBLayout implements Layout
(same — Layout is interface in Turbine 7)
Portlet Pattern
PROVEN
REAL GEB
ActionPortlet → GTPRootPortlet → AbstractPortlet
getContent(RunData) → ECS → XSL → HTML
MINI-GEB
AbstractMiniPortlet mirrors GTPRootPortlet
addGridComparator(), buildAnchorSort(), transformXSL()
PSML Parsing
PROVEN
REAL GEB
Castor XML reads portal page definitions
(BROKEN on Java 17 — Castor uses banned reflection)
MINI-GEB
dom4j replaces Castor XML — reads same .psml format
All portal pages load correctly
Velocity Usage
PROVEN
REAL GEB
ONLY TopBIBP.vm + BottomBIBP.vm (navigation chrome)
All portlet content = ECS → XSL (confirmed from .vm scan)
MINI-GEB
TopMiniGEB.vm + BottomMiniGEB.vm only
EntityListPortlet renders via XSL (no Velocity)
DB Access Pattern
PROVEN
REAL GEB
PoolBrokerService.getConnection() + StringBuffer SQL
(dominant pattern — 100s of portlets)
MINI-GEB
MiniPoolBrokerService exact same pattern
Live MySQL query — 8 entities returned
GTPParameterParser
GAP FOUND
REAL GEB
Custom parser in cfg[1] — XSS sanitization, Dojo params
Direct pool registration in Turbine 2.3.3
MINI-GEB
Cannot register custom parser in fulcrum-parser 4.0.0
Silent fallback to DefaultParameterParser

## Slide 9
Key Migration Risks — Proven Hands-On
Every finding below was reproduced live — not theoretical
GEB FCC Platform — JBoss EAP 8 Migration Assessment | Wipro Consulting × UOB Bank Singapore | Confidential
Severity
Component
Finding
Impact
Recommended Action
CRITICAL
log4j 1.2.17
Active CVE + Java 17 service loader incompatibility
Tomcat startup fails — NoSuchMethodError: ServiceLoaderUtil.loadServices()
Replace with log4j2 2.20.0+ immediately — regardless of EAP 8 timeline
CRITICAL
data.getPage()
Removed from RunData in Turbine 7
Every portlet using addGridComparator() fails to compile — all Dojo grid sorting broken across 18+ modules
Redesign page body injection pattern across all GTPRootPortlet subclasses
CRITICAL
Action / Layout API
Changed from abstract class → interface in Turbine 7
Every extends Action / extends Layout = compile error across all banking modules
Global find-replace + retest all action/layout behaviour
CRITICAL
Castor XML (PSML)
Uses banned Java 17 reflection — fails at startup
PsmlScreenManager cannot load portal pages — entire portal down
Replace with dom4j or JAXB — proven working in POC
HIGH
GTPParameterParser
Cannot be registered in fulcrum-parser 4.0.0 layer
XSS sanitization, Dojo multi-value params, encoding handling silently bypassed
Redesign parser integration layer — register via Fulcrum component config
HIGH
javax → jakarta namespace
Tomcat 10 / EAP 8 uses jakarta.* exclusively
All libraries compiled against javax.servlet.* crash — fulcrum-parser 2.0.1 proven
Upgrade all dependencies to Jakarta EE compatible versions
HIGH
Torque 3.1.1 → 5.x
Completely different Criteria API, Village ResultSet removed, ComponentService gone
All 21+ Torque imports + generated Peer classes need redesign
Assess schema.xml availability — may need regeneration of all Peer classes
HIGH
GTPSchedulerService
Implements InstanceListener — removed in Turbine 7
Compile error — all scheduled jobs stop working
Rewrite using Quartz scheduler (available in Turbine 7 / Fulcrum)
MEDIUM
JAXB removal (Java 17)
JAXB removed from JDK — must add as external dependency
Any JAXB marshalling (trade XML, SWIFT messages) breaks at runtime
Add com.sun.xml.bind:jaxb-impl dependency explicitly
MEDIUM
devtools.jar in production
Development-only JAR found in production deployment
Security exposure + potential ClassLoader conflicts in EAP 8
Remove immediately from production build

## Slide 10
JAR Compatibility Assessment — 138 Production JARs
Individually assessed for CVE severity, Java 17 readiness, Jakarta EE compatibility
GEB FCC Platform — JBoss EAP 8 Migration Assessment | Wipro Consulting × UOB Bank Singapore | Confidential
33
CRITICAL
CVE active / breaking change
52
UPGRADE
Compatible with upgrade path
28
REBUILD
Internal JARs needing recompile
12
VERIFY
Needs runtime verification
13
SAFE ✓
No changes required
🚨 IMMEDIATE ACTIONS REQUIRED (before any migration begins)
log4j-1.2.17.jar — CRITICAL CVE (CVE-2021-44228 RCE) — replace with log4j2 NOW
devtools.jar — Development JAR in production — immediate security risk
utils-SNAPSHOT.jar — SNAPSHOT in production — unstable, untested version
esapi-SNAPSHOT.jar — Security library as SNAPSHOT — critical vulnerability exposure
xalan-2.7.2.jar — Upgrade to 2.7.3 (minimum) for Java 17 compatibility
Key Upgrade Paths Identified
commons-* libraries
Apache Commons → latest Jakarta-compatible versions
Spring MVC 4.2.9
Spring 6.x (Jakarta EE) — WSService layer upgrade
Springfox Swagger
NOT compatible with Spring 6 — replace with springdoc-openapi
fulcrum-parser 2.0.1
Must upgrade to 4.0.0 (javax → jakarta namespace)
Torque 3.1.1
Full API rewrite needed — Criteria, Peer, Village all changed
ECS 1.4.2
Confirmed working on Java 21 — NO changes needed ✓

## Slide 11
Turbine Service Migration Map — What Changes, What Breaks
33 services assessed individually — colour coded by migration effort
GEB FCC Platform — JBoss EAP 8 Migration Assessment | Wipro Consulting × UOB Bank Singapore | Confidential
Service
Turbine 2.3.3
Turbine 7 Impact
Effort
Action
TurbinePoolService
org.apache.turbine.services.pool
REMOVED — moved to Fulcrum fulcrum-pool
HIGH
BREAK
TurbineFactoryService
org.apache.turbine.services.factory
REMOVED — moved to Fulcrum fulcrum-factory
HIGH
BREAK
GTPRunDataService
extends TurbineRunDataService
Requires rewrite — PipelineData + Fulcrum parser
HIGH
REWRITE
GTPSchedulerService
implements InstanceListener
InstanceListener REMOVED — rewrite with Quartz
HIGH
BREAK
GTPComponentService (DEPRECATED)
ComponentService bootstrap
Use AvalonComponentService + YAAFI instead
MED
REPLACE
EHCacheService
GlobalCacheService impl
Compatible — update EHCache version
LOW
UPGRADE
UniqueSessionService
SessionService impl
Rewrite for Turbine 7 session handling
MED
REWRITE
XSLTCachingService
TurbineXSLTService + cache
Xalan 2.7.3 drop-in — service logic compatible
LOW
UPGRADE
PortalUploadService
extends TurbineUploadService
Retest with Jakarta EE multipart
MED
VERIFY
AdapterForTurbineSecurityService
SecurityService impl
Adapter pattern still valid — test thoroughly
MED
VERIFY
TurbineVelocityService
Apache standard
Velocity 2.x API changes — template review needed
MED
UPGRADE
TurbineTemplateService
Apache standard
Turbine 7 compatible with config updates
LOW
UPGRADE
GTPAuditService
Pure GTP — no Turbine base
Minimal dependency — likely compatible
LOW
VERIFY
PsmlScreenManager
Castor XML unmarshalling
BROKEN Java 17 — replace with dom4j or JAXB
HIGH
BREAK
GTPPoolBrokerService
DB connection facade
javax.sql → jakarta.sql — one import change
LOW
UPGRADE

## Slide 12
Migration Effort & Complexity Assessment
Based on war room findings + hands-on POC validation
GEB FCC Platform — JBoss EAP 8 Migration Assessment | Wipro Consulting × UOB Bank Singapore | Confidential
Turbine Service Layer
(Layer 1–3)
EFFORT: HIGH
RISK: HIGH
TurbinePoolService removed, GTPRunDataService rewrite, InstanceListener gone
GTP Business Services
(Layer 4 — 17 services)
EFFORT: HIGH
RISK: HIGH
E2EEService, GTPPoolBrokerService, PsmlScreenManager — all need verification
Portlet / Action Layer
(300+ classes)
EFFORT: HIGH
RISK: MEDIUM
extends→implements, data.getPage() removal, RunData signature changes across every class
Torque ORM Layer
(Criteria, Peer, Village)
EFFORT: HIGH
RISK: HIGH
Complete API rewrite — no schema.xml found, Village removed, ComponentService gone
Spring / WSService Layer
(REST APIs for UOB Infinity)
EFFORT: MEDIUM
RISK: MEDIUM
Spring 4.2.9 → Spring 6 (Jakarta EE), Springfox → springdoc-openapi
XSL / Velocity Templates
(400+ XSL files)
EFFORT: LOW
RISK: LOW
Pure XML — zero Java dependency. ECS 1.4.2 confirmed working Java 21. No changes needed.
Token / E2EEService
(Kreshan/Archana — grey area)
EFFORT: UNKNOWN
RISK: HIGH
Hard/soft token, SSO integration — assessment in progress. High banking security impact.
javax → jakarta Namespace
(Full codebase scan)
EFFORT: MEDIUM
RISK: HIGH
Sakthi scanning 400+ XSL + all Java classes. Every import must be verified.
log4j → log4j2
CVE Remediation
EFFORT: LOW
RISK: CRITICAL
Replace regardless of migration. log4j 1.2.17 is active CVE. Must be done immediately.

## Slide 13
Open Items & Grey Areas Requiring Further Assessment
Items identified but needing deeper investigation before full risk quantification
GEB FCC Platform — JBoss EAP 8 Migration Assessment | Wipro Consulting × UOB Bank Singapore | Confidential
Kreshan / Archana
HIGH RISK
Token Mechanism — I-Sprint Vendor JAR Uses javax Internally
I-Sprint JARs used in the token mechanism compile against javax.* internally. This requires a vendor upgrade — outside Wipro's control. Additionally, several I-Sprint methods are deprecated in the latest version and need alternatives identified before migration can proceed.
All Teams
IN PROGRESS
GTP Param Data Family — Silent Lookup Break Risk
GTP_PARAM_DATA, GTP_LARGE_PARAM_DATA, and GTP_LARGE_PARAM_KEY are all country-code-driven lookup tables. If RunData migration changes how country code is resolved, ALL param data lookups silently return wrong values — wrong cutoff times, wrong transaction limits, wrong validations — with no exception thrown.
Gokul
IN PROGRESS
Torque 5.1 — Village Records, Peer Classes, Schema Availability
Torque 5.1 is the confirmed target (Torque 6/7 not required). However, Village ResultSet is removed in Torque 5.x — all core banking table Peer classes (generated from schema.xml) need regeneration. No schema.xml located in codebase yet. Without it, Peer regeneration is blocked and core DB operations cannot be migrated.
Sakthi
CLEAR
Trade, Trade Middle Office & Batch Modules — Upgrade Path Confirmed, No Hidden Blockers
Deep assessment of Trade Core, Trade Middle Office, and all Batch processing modules completed. No hidden framework blockers identified beyond the known Turbine 7 / Jakarta EE namespace changes already captured. Upgrade path is clear — standard migration steps apply. No proprietary third-party dependencies or custom protocol deviations found in this layer.
Akshith / Chandra
CONCLUDED
Xalan Extension Scan — 4,048 xalan:// Calls — Saxon NOT Viable
Eclipse workspace scan confirmed: 4,048 matches for xalan:// Java extension calls. 211 matches for custom Xalan security extension (GTPSecurity). 0 matches for xalan/redirect (no redirect extension used — good). Saxon HE is INCOMPATIBLE with xalan:// syntax. CONCLUSION: Xalan 2.7.3 upgrade is the ONLY viable path. Saxon cannot replace Xalan without breaking all 4,000+ extension calls.
Akshith / Chandra
HIGH
Saxon (Buildscripts Only) + Spring 4.2.9 → Spring 6 Mandatory Upgrade
Saxon: Found ONLY in buildscript XSLs (calendar.xsl, currency.xsl, number.xsl, util.xsl) — build-time only, not runtime portal. Saxon coexistence risk is isolated. Spring: WSService layer runs Spring 4.2.9 which is incompatible with Jakarta EE. Spring 6 is MANDATORY for EAP 8 — this is a HIGH effort change as Spring 6 drops all javax.* support, requires Springfox → springdoc-openapi migration, and impacts all REST API endpoints exposed to UOB Infinity.
Chandra
IN PROGRESS
Annual GreyBox Pen Test — 15 Vulnerabilities — Fixes In Progress
15 vulnerabilities identified: 5 MEDIUM (XSS post-auth, CSV/Excel Command Injection, IDOR, Privilege Escalation, CSRF) and 10 LOW (HTTP Security Headers, Cache-Control, Session Cookie in GET, Sensitive Info Disclosure, Session not invalidated on logout, Business Logic Bypass). Fixes actively in progress. XSS and Input Validation findings intersect with GTPParameterParser migration — remediation plan being aligned with migration phases.

## Slide 14
Recommendations
Evidence-based path forward — validated by hands-on POC
GEB FCC Platform — JBoss EAP 8 Migration Assessment | Wipro Consulting × UOB Bank Singapore | Confidential
01
IMMEDIATE
Address CRITICAL CVE — log4j 1.2.17 + Production JAR Hygiene
Replace log4j 1.2.17 with log4j2 2.20.0+ immediately — this is a live CRITICAL RCE vulnerability independent of EAP 8 timeline. Remove devtools.jar and all SNAPSHOT JARs from production builds. These actions carry zero migration risk and must not wait.
02
IMMEDIATE
Engage I-Sprint Vendor — javax to Jakarta EE Upgrade Required
I-Sprint token JARs depend on javax.* internally. This is a third-party vendor dependency outside Wipro's direct control. Vendor must confirm Jakarta EE compatible release availability and deprecated method alternatives. Timeline risk: if vendor cannot deliver in time, token mechanism migration becomes a project blocker.
03
SHORT TERM
Xalan 2.7.3 — Confirmed as Only XSLT Path. Proceed with Upgrade.
Scan confirmed 4,048 xalan:// Java extension calls across the XSL layer. Saxon HE is not viable. Xalan 2.7.3 is a drop-in upgrade — no XSL file changes needed. Sakthi to verify the buildscript Saxon XSLs (calendar, currency, number) are isolated from runtime portal. Upgrade can proceed with high confidence.
04
SHORT TERM
Torque 5.1 Migration — Locate Schema, Assess Village Impact on Core Tables
Torque 5.1 is the confirmed target version. Priority: locate schema.xml or confirm regeneration path for all core banking table Peers. Village ResultSet removal affects every core DB read pattern. Gokul to map all Peer classes referencing Village to quantify the full rewrite scope before migration estimate is finalised.
05
PLANNING
Migration Phasing — Framework Layer First, Business Logic Second
Phase 1: log4j2, javax→jakarta namespace, JAR upgrades, I-Sprint vendor confirmation. Phase 2: Turbine 7 service layer — RunData, PoolService, FactoryService, GTPSchedulerService. Phase 3: Portlet/Action layer — extends→implements, data.getPage() removal, 300+ classes. Phase 4: Torque 5.1 ORM redesign. Phase 5: Token/E2EEService. Phase 6: GreyBox vulnerability remediation validation.

## Slide 15
GEB FCC Platform — JBoss EAP 8 Migration Assessment | Wipro Consulting × UOB Bank Singapore | Confidential
Thank You
GEB FCC Platform — JBoss EAP 8 Migration Assessment
138 JARs Assessed · 33 Services Mapped · Mini-GEB POC Live on Turbine 7 + Java 17
Prepared by:
Wipro Consulting | Digital Engineering Practice | UOB Bank Singapore
War Room Team: Gokul · Sakthi · Akshith · Chandra · Kreshan · Archana
April 2026 · Classification: Confidential · Wipro Consulting × UOB Bank
Questions & Discussion